## HGI Project Monitoring - POS
Project Name: |  | SANGGUNIANG BAYAN INFORMATION SYSTEM |  | Project Progress (Dev) |  | 100%
Project Start: |  | 2024-10-21 |  | Project Progress (Impl) |  | 95.24%
Current Date: |  | 2026-03-11 |  | Total Progress |  | 97.62%
Weeks in Progress: |  | 73
Task | Assigned to | Process Owners | Start Date | End Date | Days | Progress | 2024-10-21 | 2024-10-28 | 2024-11-04 | 2024-11-11 | 2024-11-18 | 2024-11-25 | 2024-12-02 | 2024-12-09 | 2024-12-16 | 2024-12-23 | 2024-12-30 | 2025-01-06 | 2025-01-13 | 2025-01-20 | 2025-01-27 | 2025-02-03 | 2025-02-10 | 2025-02-17 | 2025-02-24 | 2025-03-03 | 2025-03-10 | 2025-03-17 | 2025-03-24 | 2025-03-31 | 2025-04-07 | 2025-04-14 | 2025-04-21 | 2025-04-28 | 2025-05-05 | 2025-05-12 | 2025-05-19
[7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
User Management
User Registration | Jorge Villanueva | Ms. Gail / Ms. Jacky | 2024-10-21 | 2024-10-23 | 2 | 100%
Login / authentication | Jorge Villanueva | Ms. Gail / Ms. Jacky | 2024-10-24 | 2024-10-25 | 1 | 100%
Role Management (Admin, Staff, Public User)
Password Management
User Activity Log
User Management
Users | Jorge Villanueva | Ms. Gail / Ms. Jacky | 2024-10-26 | 2024-10-29 | 3 | 100%
Users Roles | Jorge Villanueva | Ms. Gail / Ms. Jacky | 2024-10-30 | 2024-11-02 | 3 | 100%
Sales Module - Setup
Transaction Type | Jorge Villanueva | Ms. Gail / Ms. Jacky | 2024-11-03 | 2024-11-06 | 3 | 100%
Pricing Category | Jorge Villanueva | Ms. Gail / Ms. Jacky | 2024-11-07 | 2024-11-10 | 3 | 100%
Sales Module
Sales Order | Jorge Villanueva | Ms. Gail / Ms. Jacky | 2024-11-11 | 2024-11-21 | 10 | 100%
Delivery | Jorge Villanueva | Ms. Gail / Ms. Jacky | 2024-11-22 | 2024-12-02 | 10 | 100%
Receipts and Invoices | Jorge Villanueva | Ms. Gail / Ms. Jacky | 2024-12-03 | 2024-12-13 | 10 | 100%
Inventory
Item Groups | Jorge Villanueva | Ms. Gail / Ms. Jacky | 2024-12-14 | 2024-12-17 | 3 | 100%
List of Produce (Item Master Data) | Jorge Villanueva | Ms. Gail / Ms. Jacky | 2024-12-18 | 2024-12-21 | 3 | 100%
Production
Forecast | Jorge Villanueva | Ms. Gail / Ms. Jacky | 2024-12-22 | 2025-01-01 | 10 | N/A
Monitoring | Jorge Villanueva | Ms. Gail / Ms. Jacky | 2025-01-02 | 2025-01-09 | 7 | N/A
CRM
Customer List | Jorge Villanueva | Ms. Gail / Ms. Jacky | 2025-01-10 | 2025-01-13 | 3 | 100%
Sales Employee | Jorge Villanueva | Ms. Gail / Ms. Jacky | 2025-01-14 | 2025-01-17 | 3 | N/A
Leads | Jorge Villanueva | Ms. Gail / Ms. Jacky | 2025-01-18 | 2025-01-21 | 3 | N/A
Reports
Daily/Monthly/Yearly Sales Report | Jorge Villanueva | Ms. Gail / Ms. Jacky | 2025-01-22 | 2025-01-27 | 5 | 100%
Dashboard
Topselling Products | Jorge Villanueva | Ms. Gail / Ms. Jacky | 2025-01-28 | 2025-02-02 | 5 | 100%
Top 5 customers | Jorge Villanueva | Ms. Gail / Ms. Jacky | 2025-02-03 | 2025-02-08 | 5 | 100%
UAT Testing Phase One
Sales Order | Ms. Gail / Ms. Jacky | Ms. Gail / Ms. Jacky | 2025-03-17 | 2025-03-18 | 1 | 100%
Sales Approval | Ms. Gail / Ms. Jacky | Ms. Gail / Ms. Jacky | 2025-03-17 | 2025-03-18 | 1 | 100%
Fulfillment | Ms. Sheryl / Sir Jason | Ms. Sheryl / Sir Jason | 2025-03-17 | 2025-03-18 | 1 | 100%
Invoicing | Ms. Gail / Ms. Jacky | Ms. Gail / Ms. Jacky | 2025-03-17 | 2025-03-18 | 1 | 100%
Dispatching | Ms. Gail / Ms. Jacky | Ms. Gail / Ms. Jacky | 2025-03-17 | 2025-03-18 | 1 | 100%
SAP Posting | Ms. Mary Joy | Ms. Mary Joy | 2025-03-17 | 2025-03-18 | 1 | 100%
SAP Reports | Ms. Mary Joy | Ms. Mary Joy | 2025-03-17 | 2025-03-18 | 1 | 100%
Functional and Technical Updates | Jorge Villanueva | Jorge Villanueva | 2025-03-17 | 2025-03-18 | 1 | 100%
Internal Testing | Jorge Villanueva | Jorge Villanueva | 2025-03-17 | 2025-03-18 | 1 | 100%
UAT Testing Phase Two
Sales Order | Ms. Gail / Ms. Jacky | Ms. Gail / Ms. Jacky | 2025-03-27 | 2025-03-28 | 1 | 100%
Sales Approval | Ms. Gail / Ms. Jacky | Ms. Gail / Ms. Jacky | 2025-03-27 | 2025-03-28 | 1 | 100%
Fulfillment | Ms. Sheryl / Sir Jason | Ms. Sheryl / Sir Jason | 2025-03-27 | 2025-03-28 | 1 | 100%
Invoicing | Ms. Gail / Ms. Jacky | Ms. Gail / Ms. Jacky | 2025-03-27 | 2025-03-28 | 1 | 100%
Dispatching | Ms. Gail / Ms. Jacky | Ms. Gail / Ms. Jacky | 2025-03-27 | 2025-03-28 | 1 | 100%
SAP Posting | Ms. Mary Joy | Ms. Mary Joy | 2025-03-27 | 2025-03-28 | 1 | 100%
SAP Reports | Ms. Mary Joy | Ms. Mary Joy | 2025-03-27 | 2025-03-28 | 1 | 100%
Functional and Technical Updates | Jorge Villanueva | Jorge Villanueva | 2025-03-27 | 2025-03-30 | 3 | 100%
Internal Testing | Jorge Villanueva | Jorge Villanueva | 2025-03-31 | 2025-04-01 | 1 | 100%
Pre-Go Live
Go or No Go Meeting | Jorge Villanueva | All Users | 2025-07-07 | 2025-07-08 | 1 | 100%
Go Live and Support/Parallel Testing | Jorge Villanueva | All Users | 2025-07-07 | 2025-09-05 | 60 | 100%
Project Closing
Project Closing | Jorge Villanueva | All Users | 2025-09-06 | 2025-09-07 | 1 | 0%

## Backlogs
Done of the backlogs | Except of the transactions of the customer that was not yet enrolled that time | challenge about the re-opening the books
Feedback
Extraction of reports | EWT capturing, when extracting those customers with EWT | Filtering of extract the report | Ms. Joy
| Adding of SKUs Bugs | Pricing data, Salcedo B2B for Baby Romaine | Ms. Bianca
Invoice
Approvals |  |  | Ms. Katherine | E-Commerce | Landers | Salcedo's | PYC
|  |  | Ms. Katherine | B2B-C | HGI B2B Sales |  |  | Raise it to finance team
Extraction of report remove the time

## User Logs
# | Concern | Reported By | Reported Date | Assigned To | Priority Status | Status | Completed Date | Remarks
1 | Add Delivery Fees | Ms. Gail | 11/21/2024 | Jorge Villanueva | High | Completed | 11/25/2024 | For Internal Testing
2 | Add Retail Discount | Ms. Gail | 11/21/2024 | Jorge Villanueva | High | Completed | 11/25/2024 | For Internal Testing
3 | Remove Discount column in fulfillment Form | Ms. Gail | 11/21/2024 | Jorge Villanueva | Low | Completed | 11/25/2024 | For Internal Testing
4 | Additional Line for Retail and Store Discount in Fulfillment Form | Ms. Gail | 11/21/2024 | Jorge Villanueva | High | Completed | 11/25/2024 | For Internal Testing
5 | Unit of Measure in Fulfillment Form (KG/PACKS) | Ms. Gail | 11/21/2024 | Jorge Villanueva | High | Completed | 11/25/2024 | For Internal Testing
6 | Fulfilment Summary Two Export (Itemized and Totals of KG/PACKS) | Ms. Gail | 11/21/2024 | Jorge Villanueva | High | Completed
7 | Automatic filter of items base on transaction type (B2C,B2C,SUPERMARKET) | Ms. Gail | 11/21/2024 | Jorge Villanueva | Low | Completed | 2024-11-28 | For Internal Testing
8 | Additional Status (Replacement&Samples) - to trace the Bad Orders and Samples - Include previous Order | Ms. Gail | 11/21/2024 | Jorge Villanueva | High | Completed | 2024-11-29 | For Internal Testing
9 | Additional Signatories Reviewed By: | Ms. Gail | 11/21/2024 | Jorge Villanueva | High | Completed | 11/25/2024 | For Internal Testing
10 | Cancel Line Order only on Order List | Ms. Gail | 11/21/2024 | Jorge Villanueva | High | Completed |  | Cancel whole order once invoiced.
11 | Additonal Function Item Price per Category | Ms. Gail | 11/21/2024 | Jorge Villanueva | High | Completed | 2024-12-04 | For Internal Testing
12 | Additonal Function for Approval Notification ( Notification bell/message) | Ms. Gail | 11/21/2024 | Jorge Villanueva | Low | Completed | 2024-12-11 | For Internal Testing
13 | Additonal Function for Approval Notification ( Work List Items for Pending Approvals) | Ms. Gail | 11/21/2024 | Jorge Villanueva | Low | Completed | 2024-10-01 | For Internal Testing
14 | Everytime there is a discount it should routed for approvals Sales Lead, BU Leads | Ms. Nerissa | 12/13/2024 | Jorge Villanueva | Low | Pending - Next Feature |  | To be developed after the critical Modules is completed
15 | One time set-up - Price Category (Control of uploading the prices (need to have a valid documents MEMO) | Ms. Nerissa | 12/13/2024 | Jorge Villanueva | Low | Pending - Next Feature |  | To be developed after the critical Modules is completed
16 | Effective dates of pricing set-up | Sir. Sonny | 12/13/2024 | Jorge Villanueva | Low | Pending - Next Feature |  | To be developed after the critical Modules is completed
17 | Packaging - per SKU - During Packing | Ms. Nerissa | 12/13/2024 | Jorge Villanueva | Low | Pending - Next Feature |  | To be developed after the critical Modules is completed
18 | certain standards for Dates (Print Out) | Sir. Sonny | 12/13/2024 | Jorge Villanueva | Low | Completed |  | To be developed after the critical Modules is completed
19 | Continue with the cut-over - of Sales Order Number (QR Code - Bar Code) | Sir Alfonso | 12/13/2024 | Jorge Villanueva | Low | Completed |  | Set-up Numbering series during go live
20 | When the invoices is printed no mpore updates. | Ms. Nerissa | 12/13/2024 | Jorge Villanueva | Low | Completed | 2024-10-01 | For Internal Testing
21 | Order can be updated if the order doesn’t have an Invoice yet. | Ms. Nerissa | 12/13/2024 | Jorge Villanueva | Low | Completed |  | To be developed after the critical Modules is completed
22 | Fulfilment SUmmary with Period From and Period to Filtering | Ms. Sheryl | 2025-07-11 | Jorge Villanueva | High | Completed
23 | Fulfillment Batch Printing per Branch Only | Ms. Bianca | 2025-07-11 | Jorge Villanueva | High | Completed
24 | Rejected Orders must be routed back to Approver after updating | Ms. Gail | 2025-07-11 | Jorge Villanueva | High | Completed
25 | Finance and Admin must be able to cancel after encoding | Ms. Bianca | 2025-07-11 | Jorge Villanueva | High | Completed
26 | Filtering in List of Order | Ms. Bianca | 2025-07-11 | Jorge Villanueva | Medium | Completed
27 | Additional PO number during approval | Ms. Gail | 2025-07-11 | Jorge Villanueva | Low | Completed
28 | Tagum Invoice Printing | Ms. Jacky | 2025-07-11 | Jorge Villanueva | High | Completed |  | For testing
29 | Additional functionality for consignment (add button during updates) | Ms. Gail | 2025-07-11 | Jorge Villanueva | Medium | Completed
30 | Changing status from delivery to Dispatch for filtering | Sir Jake | 2025-07-11 | Jorge Villanueva | Low | Completed
31 | Merging of orders, Invoice | Ms. Gail | 2025-08-27 | Jorge Villanueva | Low | Pending - Next Feature |  | Not Applicable
32 | Adding dates on Fulfillment Summary Report | Ms. Sheryl | 2025-08-13 | Jorge Villanueva | Low | Pending
33 | Adding system indicator that the invoices was received by the admin after sending it to the customer | Ms. Bianca | 2025-08-13 | Jorge Villanueva | Low | Pending
34 | Additional Summary Report for Dispatched List | Ms. Gail | 2025-08-27 | Jorge Villanueva | Low | Completed
35 | Error functionality when adding new order, in List of Order | Ms. Bianca | 2025-08-27 | Jorge Villanueva | High | Completed
36 | Filtering in Sales Report | Ms. Mary Joy | 2025-08-27 | Jorge Villanueva | Low | Completed |  | For Deployment
37 | Extract Sales Report Include Customer Wheld Tax | Ms. Mary Joy | 2025-08-27 | Jorge Villanueva | Low | Pending |  | Currrently working on
38 | Sales Order Remarks Remove the old SI Number | Ms. Mary Joy | 2025-10-09 | Jorge Villanueva | Medium | Completed |  | Deployed
39 | Greenhouse tagging during sales order encoding | Ms. Mary Joy | 2025-11-10 | Jorge Villanueva | High | Completed |  | For Deployment
40 | Batch Printing for Pending Order | Ms. Gail | 2025-11-19 | Jorge Villanueva | Medium | Completed |  | For Deployment
41 | Price Category Update Pricing A & Pricing B - Dec. 15. | Ms. Gail | 2025-11-20 | Jorge Villanueva | High | Pending |  | Currrently working on
Remarks Salcedo during SAP posting./ Manual encoding of landers remarks is not showing
Ms. Nery approver of Mothers choice
Segragation of approval

## Risk Register
ID | RISK DESCRIPTION | LIKELIHOOD | SEVERITY | RISK FACTOR | OWNER | MITIGATING ACTION | CONTINGENT ACTION | PROGRESS ON ACTIONS | USEFUL RESOURCES
1 | Data migration errors during system implementation. | High | High | High | Project Manager | Conduct thorough testing and validation of migrated data. | Roll back migration and investigate issues. | Validate the data | Data migration checklist
2 | User resistance to adopting the new system. | High | High | High | Change Management Lead | Provide comprehensive training and support materials. | Offer one-on-one sessions for resistant users. | Develop a training Plan | Training schedule and materials
3 | Potential data security breaches during implementation | High | High | High | Technical Lead | Implement strict security protocols and audits. | Activate incident response plan | Security protocols in place | Incident response policy
4 | Budget Constraints | Low | High | Medium | Project Manager | Conduct regular budget reviews and consider phased implementation to spread costs over time. | Identify and focus on high-impact project deliverables and eliminate non-essential features or functionalities to reduce costs. | Budget Tracking | Budget Tracking Tool