## SIS Project Monitoring
| Project Name: | SANGGUNIAN INFORMATION SYSTEM |  | Project Progress (Dev) |  | 0%
| Project Start: | 2026-03-23 |  | Project Progress (Impl) |  | 0%
| Current Date: | 2026-03-11 |  | Total Progress |  | 0%
| Weeks in Progress: | -2
| Total Man Days: | 70
Task | Assigned to | Process Owners | Start Date | End Date | Days | Progress | 2026-03-23 | 2026-03-30 | 2026-04-06 | 2026-04-13 | 2026-04-20 | 2026-04-27 | 2026-05-04 | 2026-05-11 | 2026-05-18 | 2026-05-25 | 2026-06-01 | 2026-06-08 | 2026-06-15 | 2026-06-22 | 2026-06-29 | 2026-07-06 | 2026-07-13 | 2026-07-20 | 2026-07-27 | 2026-08-03 | 2026-08-10 | 2026-08-17 | 2026-08-24 | 2026-08-31 | 2026-09-07 | 2026-09-14 | 2026-09-21 | 2026-09-28 | 2026-10-05 | 2026-10-12 | 2026-10-19
[7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
1. User Management |  |  |  |  | 7
1.1 User Registration | Programmer | MGO Officer | 2026-03-23 | 2026-03-25 | 2 | 0%
1.2 Login / authentication | Programmer | MGO Officer | 2026-03-26 | 2026-03-28 | 2 | 0%
1.3 Role Management (Admin, Staff, Public User) | Programmer | MGO Officer | 2026-03-29 | 2026-03-30 | 1 | 0%
1.4 Password Management | Programmer | MGO Officer | 2026-03-31 | 2026-04-01 | 1 | 0%
1.5 User Activity Log | Programmer | MGO Officer | 2026-04-02 | 2026-04-03 | 1 | 0%
2. Document Registration |  |  |  |  | 7
2.1 Add new document record | Programmer | MGO Officer | 2026-04-04 | 2026-04-06 | 2 | 0%
2.2 Upload scanned document (PDF/Image) | Programmer | MGO Officer | 2026-04-07 | 2026-04-10 | 3 | 0%
2.3 Assign document type | Programmer | MGO Officer | 2026-04-11 | 2026-04-12 | 1 | 0%
2.4 Assign document category | Programmer | MGO Officer | 2026-04-13 | 2026-04-14 | 1 | 0%
3. Document Storage |  |  |  |  | 4
3.1 File storage management | Programmer | MGO Officer | 2026-04-15 | 2026-04-17 | 2 | 0%
3.2 Document update | Programmer | MGO Officer | 2026-04-18 | 2026-04-19 | 1 | 0%
3.3 Document archive | Programmer | MGO Officer | 2026-04-20 | 2026-04-21 | 1 | 0%
4. Document Search and Retrieval |  |  |  |  | 7
4.1 Document Searching (Document Name, Reference number, Category, Keywords, Date) | Programmer | MGO Officer | 2026-04-22 | 2026-04-25 | 3 | 0%
4.2 Display search results | Programmer | MGO Officer | 2026-04-26 | 2026-04-28 | 2 | 0%
4.3 Open/view document | Programmer | MGO Officer | 2026-04-29 | 2026-04-30 | 1 | 0%
4.4 Download document (optional) | Programmer | MGO Officer | 2026-05-01 | 2026-05-02 | 1 | 0%
5. Physical Location Tracking |  |  |  |  | 4
5.1 Encode storage location (Cabinet, Drawer, Box, Folder) | Programmer | MGO Officer | 2026-05-03 | 2026-05-05 | 2 | 0%
5.2 Update document location | Programmer | MGO Officer | 2026-05-06 | 2026-05-07 | 1 | 0%
5.3 Display physical storage location when searched | Programmer | MGO Officer | 2026-05-08 | 2026-05-09 | 1 | 0%
6. Public Access Portal |  |  |  |  | 5
6.1 Public document search | Programmer | MGO Officer | 2026-05-10 | 2026-05-12 | 2 | 0%
6.2 View document information | Programmer | MGO Officer | 2026-05-13 | 2026-05-14 | 1 | 0%
6.3 View scanned document (if allowed) | Programmer | MGO Officer | 2026-05-15 | 2026-05-16 | 1 | 0%
6.4 Limited access permissions | Programmer | MGO Officer | 2026-05-17 | 2026-05-18 | 1 | 0%
7. Document Classification |  |  |  |  | 4
7.1 Manage document categories | Programmer | MGO Officer | 2026-05-19 | 2026-05-21 | 2 | 0%
7.2 Manage document types | Programmer | MGO Officer | 2026-05-22 | 2026-05-23 | 1 | 0%
7.3 Tagging keywords | Programmer | MGO Officer | 2026-05-24 | 2026-05-25 | 1 | 0%
8. Reports and Monitoring |  |  |  |  | 5
8.1 Document inventory report | Programmer | MGO Officer | 2026-05-26 | 2026-05-28 | 2 | 0%
8.2 Recently added documents | Programmer | MGO Officer | 2026-05-29 | 2026-05-30 | 1 | 0%
8.3 Search history | Programmer | MGO Officer | 2026-05-31 | 2026-06-01 | 1 | 0%
8.4 Activity logs | Programmer | MGO Officer | 2026-06-02 | 2026-06-03 | 1 | 0%
9. System Testing |  |  |  |  | 7
9.1 Unit testing (per module) | Programmer | MGO Officer | 2026-06-04 | 2026-06-06 | 2 | 0%
9.2 Integration testing | Programmer | MGO Officer | 2026-06-07 | 2026-06-08 | 1 | 0%
9.3 File upload testing | Programmer | MGO Officer | 2026-06-09 | 2026-06-11 | 2 | 0%
9.4 Search functionality testing | Programmer | MGO Officer | 2026-06-12 | 2026-06-13 | 1 | 0%
9.5 Bug fixing | Programmer | MGO Officer | 2026-06-14 | 2026-06-15 | 1 | 0%
10. Implementation |  |  |  |  | 5
10.1 System installation on server | Programmer | MGO Officer | 2026-06-16 | 2026-06-17 | 1 | 0%
10.2 Database deployment | Programmer | MGO Officer | 2026-06-18 | 2026-06-19 | 1 | 0%
10.3 Upload initial documents | Programmer | MGO Officer | 2026-06-20 | 2026-06-21 | 1 | 0%
10.4 User account setup | Programmer | MGO Officer | 2026-06-22 | 2026-06-23 | 1 | 0%
10.5 Staff orientation | Programmer | MGO Officer | 2026-06-24 | 2026-06-25 | 1 | 0%
11. Pre-Go-Live |  |  |  |  | 6
11.1 Final system review | Programmer | MGO Officer | 2026-06-26 | 2026-06-27 | 1 | 0%
11.2 User Acceptance Testing (UAT) | Programmer | MGO Officer | 2026-06-28 | 2026-06-29 | 1 | 0%
11.3 Staff hands-on testing | Programmer | MGO Officer | 2026-06-30 | 2026-07-01 | 1 | 0%
11.4 Final bug fixes | Programmer | MGO Officer | 2026-07-02 | 2026-07-03 | 1 | 0%
11.5 Data verification | Programmer | MGO Officer | 2026-07-04 | 2026-07-05 | 1 | 0%
11.6 System performance check | Programmer | MGO Officer | 2026-07-06 | 2026-07-07 | 1 | 0%
12. Go-Live |  |  |  |  | 4
12.1 Official system launch | Programmer | MGO Officer | 2026-07-08 | 2026-07-09 | 1 | 0%
12.2 Records department begins using system | Programmer | MGO Officer | 2026-07-10 | 2026-07-11 | 1 | 0%
12.3 Monitor system performance | Programmer | MGO Officer | 2026-07-12 | 2026-07-13 | 1 | 0%
12.4 Immediate support | Programmer | MGO Officer | 2026-07-14 | 2026-07-15 | 1 | 0%
13. Post-Implementation Support |  |  |  |  | 4
13.1 User support | Programmer | MGO Officer | 2026-07-17 | 2026-07-18 | 1 | 0%
13.2 Minor bug fixes | Programmer | MGO Officer | 2026-07-19 | 2026-07-20 | 1 | 0%
13.3 System adjustments | Programmer | MGO Officer | 2026-07-21 | 2026-07-22 | 1 | 0%
13.4 Final documentation | Programmer | MGO Officer | 2026-07-23 | 2026-07-24 | 1 | 0%
Project Closing |  |  |  |  | 1
Project Closing | Programmer | MGO Officer | 2026-07-25 | 2026-07-26 | 1 | 0%

## Backlogs
Extraction of report remove the time

## User Logs
# | Concern | Reported By | Reported Date | Assigned To | Priority Status | Status | Completed Date | Remarks

## Risk Register
ID | RISK DESCRIPTION | LIKELIHOOD | SEVERITY | RISK FACTOR | OWNER | MITIGATING ACTION | CONTINGENT ACTION | PROGRESS ON ACTIONS | USEFUL RESOURCES
1 | Data migration errors during system implementation. | High | High | High | Project Manager | Conduct thorough testing and validation of migrated data. | Roll back migration and investigate issues. | Validate the data | Data migration checklist
2 | User resistance to adopting the new system. | High | High | High | Change Management Lead | Provide comprehensive training and support materials. | Offer one-on-one sessions for resistant users. | Develop a training Plan | Training schedule and materials
3 | Potential data security breaches during implementation | High | High | High | Technical Lead | Implement strict security protocols and audits. | Activate incident response plan | Security protocols in place | Incident response policy
4 | Budget Constraints | Low | High | Medium | Project Manager | Conduct regular budget reviews and consider phased implementation to spread costs over time. | Identify and focus on high-impact project deliverables and eliminate non-essential features or functionalities to reduce costs. | Budget Tracking | Budget Tracking Tool